## ML
Tanggal | Progres | Minggu I | Minggu II | Minggu III | Minggu IV | Minggu V
2023-05-03 | Searching for literature and github repository related to existing problems
2023-05-04 | Determine the goals and objectives of the project
2023-05-05 | Design ideas related to existing problems
2023-05-06 | Do research on the problem at hand
2023-05-07 | Looking for datasets
2023-05-08 | Python connectivity experiment with SQL
2023-05-11 | Preparation tools for making modeling
2023-05-12 | Data preparation for modeling
2023-05-14 | Model creation uses CNN deep learning
2023-05-19 | Conduct training with the model that has been made
2023-05-20 | Analyze graph accuracy and overfitting
2023-05-21 | Project monitoring and adjustment
2023-05-22 | Evaluation and improvement
2023-05-23 | Deploy models to the system
2023-05-24 | File archiving project documentation
2023-05-25 | Report generation
2023-05-26 | Making PowerPoint for presentation
2023-05-27 | Making video presentations

## CC
Tanggal | Progres | Minggu I | Minggu II | Minggu III | Minggu IV | Minggu V
2023-05-03 | Searching for literature and github repository related to existing problems
2023-05-04 | Determine the goals and objectives of the project
2023-05-05 | Design ideas related to existing problems
2023-05-06 | Do research on the problem at hand
2023-05-07 | Looking for Datasets
2023-05-09 | Xampp connectivity with localhost
2023-05-10 | Make a website display design (Dashboard)
2023-05-13 | Create a simple website to display modeling results
2023-05-15 | CRUD implementation on websites
2023-05-16 | Test Connection Website with Database
2023-05-17 | Testing whether the Website and Database are connected properly
2023-05-18 | Linking Website with hosting
2023-05-22 | Evaluation and improvement
2023-05-23 | Deploy models to the system
2023-05-24 | File archiving project documentation
2023-05-25 | Report generation
2023-05-26 | Making PowerPoint for presentation
2023-05-27 | Making video presentations

## Deskripsi
Tanggal | Kegiatan | Deskripsi | Role | Penanggung Jawab
2023-05-03 | Menentukan sasaran dan tujuan dari project | Tim menerapkan management project berupa inisiasi agar mendapatkan tujuan dan sasaran dari project |  | Asnan Sabil | Iis Ismail
|  |  |  | Iis Ismail | Luthfi Fadhlurrohman
Luthfi D Fadhlurrohman
|  |  |  | Arif Hidayat | Arif Hidayat
2023-05-04 | Mencari literatur terkait permasalahan yang ada |  |  | Asnan Sabil
2023-05-05 | Perancangan ide terkait permaalahan yang ada |  |  | Iis Ismail
Luthfi Fadhlurrohman
Arif Hidayat
Asnan Sabil
Iis Ismail
Luthfi Fadhlurrohman
Arif Hidayat